## Strategy Overview
PROPVR — 6-Month Marketing Content Plan (Apr 20 – Oct 18, 2026)
Rebranding → Launch → Product Push → Deepening → Lead Generation
OVERVIEW
Period | April 20 – October 18, 2026 (26 weeks / 6 months)
Launch Date | Monday April 20, 2026 — Spatial Ecosystem Rebrand
Markets | UAE, Saudi Arabia, India
Primary Focus | Real Estate (3D visualization for developers, brokers, hospitality)
JOURNEY ARC — 4 PHASES
Phase 1: REBRAND + LAUNCH (W1–W4) | Spatial Ecosystem reveal + Lite, World, Twin
Phase 2: PRODUCT PUSH (W5–W11) | Guide, Cave, Table, Touch, Tour, Holo, Agent
Phase 3: DEEPENING + CASE STUDIES (W12–W18) | Cases, testimonials, ROI, EC tours, bundles
Phase 4: LEAD GENERATION (W19–W26) | Demos, webinars, retargeting, sales push, Q4 early access
PRIORITY PRODUCT LAUNCH ORDER
W1 | 🚀 Spatial OS Ecosystem (rebrand umbrella)
W2 | Spatial Lite
W3 | Spatial World
W4 | Spatial Twin (FLAGSHIP)
W5 | Spatial Guide
W6 | Spatial Cave
W7 | Spatial Table
W8 | Spatial Touch
W9 | Spatial Tour
W10 | Spatial Holo (hero product)
W11 | Spatial Agent
INSERTED SPECIAL POSTS
Holidays & Festivals | 7 posts across all 4 social channels (Labour Day, Eid al-Adha, Environment Day, Islamic New Year, Indian Independence Day, Saudi National Day, Gandhi Jayanti)
Founder's Notes | 6 monthly founder videos/notes — launch reflection, industry perspective, milestone check-ins
Work Culture Posts | 6 monthly culture posts — team spotlights, BTS, hiring, values, celebrations
Content Services (clubbed) | 6 monthly clubbed Content Studio showcases — 3D Rendering + Animation + 360° + VR Movies + XR as ONE post, not separate
Industry Whitepaper Drops | 13 drops, every 2 weeks — generic, real-estate-adjacent, not deeply tied to all products
CONTENT FORMAT EMPHASIS (real estate 3D viz)
Instagram | Reels heavy — 70% Reels, 20% Carousels, 10% Static
LinkedIn | 50% video/reel, 30% carousel, 20% long-form text
Facebook | 40% video/reel, 40% carousel, 20% text+image
X (Twitter) | Short text + 1 image/GIF per post
Blog | Long-form SEO articles, embedded videos
Newsletter | Video-embedded emails with strong CTAs
CHANNEL BASE SCHEDULE
LinkedIn | 2× per week — Tuesday & Thursday
X (Twitter) | 3× per week — Monday, Wednesday, Friday
Instagram | 3× per week — Monday, Wednesday, Friday (Reels-first)
Facebook | 3× per week — Tuesday, Thursday, Saturday
Blog | Weekly — Wednesday
Newsletter | Weekly — Friday
PROMO RULES
Blog Promo | Every blog (Wed) gets social promo on Thursday
Newsletter Promo | Every newsletter (Fri) gets social promo on Saturday
Whitepaper Drop | Every 2 weeks — gated LinkedIn + email + retargeting ad
Holiday Posts | Posted across LinkedIn + X + Instagram + Facebook on festival day
SCOPE NOTE | Gaming (Nite Realm) and Project Launches services are EXCLUDED from this plan.
Industry Content | Generic & real-estate-adjacent — not deeply tied to all Spatial products.
Content Services | Clubbed into ONE monthly showcase, not individual service posts.
🚀 MONTH 1 LAUNCH CAMPAIGN — DAILY LINKEDIN
Pre-Launch Teasers | Apr 16–19 (4 days) — daily excitement build-up
Daily LinkedIn — Launch + Month | Apr 20 – May 19 (30 days) — see 'Launch Campaign Month 1' sheet for full daily schedule
Reveal Order | Ecosystem → Products → EC Hardware → Solutions → Content Services → Founder's Note → Industries → Culture → Recap
Post Cadence Reverts | After May 19, LinkedIn returns to standard Tue/Thu cadence per main plan
Other Channels (X/Insta/FB) | Continue standard schedule; cross-post holiday (May 1) across all 4 channels

## Content Calendar
📅 DAILY CONTENT PLAN — One Topic Per Day, All Platforms
Each day = one topic across LinkedIn · X · Instagram · Facebook · Blog · Newsletter ¦ 3 posting days/week (Mon/Wed/Fri) + 4 pre-launch days
Day # | Date | Day | Week | Phase | Daily Topic | LinkedIn | LI Format | X (Twitter) | X Format | Instagram | IG Format | Facebook | FB Format | Blog | Newsletter | Content Creator | Storyboard Creator | Video Editor | Task
1 | Apr 16 | Thu | W0 | Phase 1: Rebrand + Launch | Teaser Day 1: 4 days to go — something big is coming from PROPVR | Teaser Day 1: 4 days to go — something big is coming from PROPVR | Post | Teaser Day 1: 4 days to go — something big is coming from PROPVR | Post | Teaser Day 1: 4 days to go — something big is coming from PROPVR | Reel | Teaser Day 1: 4 days to go — something big is coming from PROPVR | Post |  |  | Abhirami | — | — | Completed
2 | Apr 17 | Fri | W0 | Phase 1: Rebrand + Launch | Teaser Day 2: 3 days to go — the future of real estate viz is near | Teaser Day 2: 3 days to go — the future of real estate viz is near | Post | Teaser Day 2: 3 days to go — the future of real estate viz is near | Post | Teaser Day 2: 3 days to go — the future of real estate viz is near | Reel | Teaser Day 2: 3 days to go — the future of real estate viz is near | Post |  |  | Abhirami | — | — | Completed
3 | Apr 18 | Sat | W0 | Phase 1: Rebrand + Launch | Teaser Day 3: 2 days to go — countdown hype Post | Teaser Day 3: 2 days to go — countdown hype | Post | Teaser Day 3: 2 days to go — countdown hype | Post | Teaser Day 3: 2 days to go — countdown hype | Post | Teaser Day 3: 2 days to go — countdown hype | Post |  |  | Abhirami | — | — | Completed
4 | Apr 19 | Sun | W0 | Phase 1: Rebrand + Launch | Teaser Day 4: Tomorrow we unveil the Spatial Ecosystem | Teaser Day 4: Tomorrow we unveil the Spatial Ecosystem | Post | Teaser Day 4: Tomorrow we unveil the Spatial Ecosystem | Post | Teaser Day 4: Tomorrow we unveil the Spatial Ecosystem | Reel | Teaser Day 4: Tomorrow we unveil the Spatial Ecosystem | Post |  |  | Abhirami | — | — | Completed
5 | Apr 20 | Mon | W1 | Phase 1: Rebrand + Launch | 🚀 Spatial Ecosystem is LIVE (launch video, pinned) | 🚀 Spatial Ecosystem is LIVE (launch video, pinned) | Video | 🚀 Spatial Ecosystem is LIVE (launch video, pinned) | Post | 🚀 Spatial Ecosystem is LIVE (launch video, pinned) | Reel | 🚀 Spatial Ecosystem is LIVE (launch video, pinned) | Video |  |  | Abhirami | Sanath, Abhirami | Sooriya | Completed
| Apr 21 | Tue | W1 | Phase 1: Rebrand + Launch | How Spatial OS connects everything | How Spatial OS connects everything | Carousel | [8 empty] | Abhirami | — | — | Completed
6 | Apr 22 | Wed | W1 | Phase 1: Rebrand + Launch | Welcome to the Spatial Ecosystem — PROPVR's rebrand (22 Apr) | Welcome to the Spatial Ecosystem — PROPVR's rebrand (22 Apr) | Blog | Welcome to the Spatial Ecosystem — PROPVR's rebrand (22 Apr) | Blog | [5 empty] | Welcome to the Spatial Ecosystem — PROPVR's rebrand (23 Apr) | Abhirami | — | — | Completed
7 | Apr 24 | Fri | W1 | Phase 1: Rebrand + Launch | PROPVR Expereince Center | PROPVR Expereince Center | Carousel |  |  | PROPVR Expereince Center | Carousel | PROPVR Expereince Center | Carousel |  |  | Abhirami | — | — | Completed
8 | Apr 27 | Mon | W2 | Phase 1: Rebrand + Launch | Spatial Lite: web-based immersive portfolios, no downloads (demo reel) | Spatial Lite: web-based immersive portfolios, no downloads (demo reel) | Video | Spatial Lite: web-based immersive portfolios, no downloads (demo reel) | Post | Spatial Lite: web-based immersive portfolios, no downloads (demo reel) | Reel | Spatial Lite: web-based immersive portfolios, no downloads (demo reel) | Video |  |  | Abhirami | Sanath | Sooriya
12 | Apr 28 | Tue | W2 | Phase 1: Rebrand + Launch | Spatial World: Turning Portfolios into Explorable Worlds- Founder post reposting | Spatial World: Turning Portfolios into Explorable Worlds | Post | Spatial World: Turning Portfolios into Explorable Worlds | Post | Spatial World: Turning Portfolios into Explorable Worlds | Post | Spatial World: Turning Portfolios into Explorable Worlds | Post |  |  | Ankita | — | —
14 | Apr 29 | Wed | W2 | Phase 1: Rebrand + Launch | Spatial Twin: our flagship. Real-time photoreal 3D (flagship demo video) | Spatial Twin: our flagship. Real-time photoreal 3D (flagship demo video) | Video | Spatial Twin: our flagship. Real-time photoreal 3D (flagship demo video) | Post | Spatial Twin: our flagship. Real-time photoreal 3D (flagship demo video) | Reel | Spatial Twin: our flagship. Real-time photoreal 3D (flagship demo video) | Video |  |  | Abhirami | Sanath | Sooriya
9 | Apr 30 | Thu | W2 | Phase 1: Rebrand + Launch | Experience center products - Blog | Experience center products - Blog Promo | Post | Experience center products - Blog Promo | Post | [5 empty] | Experience center products - Blog | Abhirami | — | —
10 | May 1 | Fri | W2 | Phase 1: Rebrand + Launch | Product Spotlight: Spatial Cave — The Immersive Room | Product Spotlight: Spatial Cave — The Immersive Room | Post | Product Spotlight: Spatial Cave — The Immersive Room | Post | Product Spotlight: Spatial Cave — The Immersive Room | Reel | Product Spotlight: Spatial Cave — The Immersive Room | Post |  | Product Spotlight: Spatial Cave — The Immersive Room (29 May) | Ankita | — | —
11 | May 4 | Mon | W2 | Phase 1: Rebrand + Launch | Spatial Guide: remote property tours, live video + 3D (live demo) | Spatial Guide: remote property tours, live video + 3D (live demo) | Carousel | Spatial Guide: remote property tours, live video + 3D (live demo) | Carousel | Spatial Guide: remote property tours, live video + 3D (live demo) | Carousel | Spatial Guide: remote property tours, live video + 3D (live demo) | Carousel |  |  | Ankita | — | —
12 | May 5 | Tue | W2 | Phase 1: Rebrand + Launch | Puravankara - KVN Northern lights - Spatial Cave - Immersive room- Experience video | Puravankara - KVN Northern lights - Spatial Cave - Immersive room- Experience video | Video | Puravankara - KVN Northern lights - Spatial Cave - Immersive room- Experience video | Video | Puravankara - KVN Northern lights - Spatial Cave - Immersive room- Experience video | Video | Puravankara - KVN Northern lights - Spatial Cave - Immersive room- Experience video | Video |  |  | Abhirami | Sanath | Sooriya
| May 6 | Wed | W2 | Phase 1: Rebrand + Launch | Spatial Avatar: AI avatar inside a Holobox, multilingual - Post | Spatial Agent: AI avatar inside a Holobox, multilingual | Post | Spatial Agent: AI avatar inside a Holobox, multilingual | Post | Spatial Agent: AI avatar inside a Holobox, multilingual | Post | Spatial Agent: AI avatar inside a Holobox, multilingual | Post |  |  | Ankita | — | —
| May 7 | Thu | W2 | Phase 1: Rebrand + Launch | Spatial Cities: | Spatial Cities turns master plans into navigable 3D cities — perfect for giga-projects | Post | Spatial Cities: see entire master plans in 3D before a brick is laid. Built for giga-projects. | Post | [6 empty] | Ankita | — | —
13 | May 8 | Fri | W3 | Phase 1: Rebrand + Launch | Spatial Agent: | Spatial Agent: AI-powered property concierge inside a Holobox — speaks 40+ languages | Post | Spatial Agent: imagine an AI concierge that sells property in 40+ languages, 24/7. | Post | [6 empty] | Ankita | — | —
15 | May 13 | Wed | W4 | Phase 1: Rebrand + Launch | Spatial Twin: Why Real-Time 3D Walkthroughs Sell Property (13 May) | Spatial Twin: Why Real-Time 3D Walkthroughs Sell Property (13 May) | Post | Spatial Twin: Why Real-Time 3D Walkthroughs Sell Property (13 May) | Post | Spatial Twin: Why Real-Time 3D Walkthroughs Sell Property (13 May) | Reel | Spatial Twin: Why Real-Time 3D Walkthroughs Sell Property (13 May) | Post | Spatial Twin: Why Real-Time 3D Walkthroughs Sell Property (13 May) |  | Ankita | — | —
16 | May 15 | Fri | W4 | Phase 1: Rebrand + Launch | Product Spotlight: Spatial Twin — The Flagship (15 May) | Product Spotlight: Spatial Twin — The Flagship (15 May) | Post | Product Spotlight: Spatial Twin — The Flagship (15 May) | Post | Product Spotlight: Spatial Twin — The Flagship (15 May) | Reel | Product Spotlight: Spatial Twin — The Flagship (15 May) | Post |  | Product Spotlight: Spatial Twin — The Flagship (15 May) | Abhirami | — | —
17 | May 18 | Mon | W5 | Phase 2: Product Push | Spatial Guide: Remote Property Tours — Live Video + 3D Walkthrough | Spatial Guide: remote property tours — live video + 3D walkthrough demo | Video | Spatial Guide: show properties to buyers across 3 countries without leaving your desk. | Post | Reel: Spatial Guide — remote tour demo | Reel | Spatial Guide: remote property tours live | Video |  |  | Ankita | Sanath | Sooriya
18 | May 20 | Wed | W5 | Phase 2: Product Push | Spatial Guide: How Remote Sales Tours Close Deals (20 May) | Spatial Guide: How Remote Sales Tours Close Deals (20 May) | Post | Spatial Guide: How Remote Sales Tours Close Deals (20 May) | Post | Spatial Guide: How Remote Sales Tours Close Deals (20 May) | Reel | Spatial Guide: How Remote Sales Tours Close Deals (20 May) | Post | Spatial Guide: How Remote Sales Tours Close Deals (20 May) |  | Abhirami | — | —
19 | May 22 | Fri | W5 | Phase 2: Product Push | Product Spotlight: Spatial Guide — Sales Anywhere (22 May) | Product Spotlight: Spatial Guide — Sales Anywhere (22 May) | Post | Product Spotlight: Spatial Guide — Sales Anywhere (22 May) | Post | Product Spotlight: Spatial Guide — Sales Anywhere (22 May) | Reel | Product Spotlight: Spatial Guide — Sales Anywhere (22 May) | Post |  | Product Spotlight: Spatial Guide — Sales Anywhere (22 May) | Ankita | — | —
20 | May 25 | Mon | W6 | Phase 2: Product Push | Spatial Cave: immersive LED + projection room, 1:1 scale (walkthrough reel) | Spatial Cave: immersive LED + projection room, 1:1 scale (walkthrough reel) | Video | Spatial Cave: immersive LED + projection room, 1:1 scale (walkthrough reel) | Post | Spatial Cave: immersive LED + projection room, 1:1 scale (walkthrough reel) | Reel | Spatial Cave: immersive LED + projection room, 1:1 scale (walkthrough reel) | Video |  |  | Abhirami | Sanath | Sooriya
21 | May 27 | Wed | W6 | Phase 2: Product Push | Spatial Cave: Inside the Immersive Room (27 May) | Spatial Cave: Inside the Immersive Room (27 May) | Post | Spatial Cave: Inside the Immersive Room (27 May) | Post | Spatial Cave: Inside the Immersive Room (27 May) | Reel | Spatial Cave: Inside the Immersive Room (27 May) | Post | Spatial Cave: Inside the Immersive Room (27 May) |  | Ankita | — | —
22 | May 29 | Fri | W6 | Phase 2: Product Push | Spatial Agent: AI avatar inside a Holobox, multilingual (AI demo video) | Spatial Agent: AI avatars in a Holobox — multilingual, always-on property concierge | Post | Spatial Agent: your AI sales rep never sleeps, speaks every language, and lives in a Holobox. | Post | Reel: Spatial Agent AI demo — multilingual conversation | Reel | Spatial Agent: AI property concierge demo — see it in action | Post |  |  | Ankita | — | —
23 | Jun 1 | Mon | W7 | Phase 2: Product Push | Spatial Table: tangible + touch + projection (hands-on demo reel) | Spatial Table: tangible + touch + projection (hands-on demo reel) | Video | Spatial Table: tangible + touch + projection (hands-on demo reel) | Post | Spatial Table: tangible + touch + projection (hands-on demo reel) | Reel | Spatial Table: tangible + touch + projection (hands-on demo reel) | Video |  |  | Abhirami | Sanath | Sooriya
24 | Jun 3 | Wed | W7 | Phase 2: Product Push | Spatial Table: The Interactive Tangible Model (3 Jun) | Spatial Table: The Interactive Tangible Model (3 Jun) | Post | Spatial Table: The Interactive Tangible Model (3 Jun) | Post | Spatial Table: The Interactive Tangible Model (3 Jun) | Reel | Spatial Table: The Interactive Tangible Model (3 Jun) | Post | Spatial Table: The Interactive Tangible Model (3 Jun) |  | Ankita | — | —
25 | Jun 5 | Fri | W7 | Phase 2: Product Push | Product Spotlight: Spatial Table — Interactive Tangible (5 Jun) | Product Spotlight: Spatial Table — Interactive Tangible (5 Jun) | Post | Product Spotlight: Spatial Table — Interactive Tangible (5 Jun) | Post | Product Spotlight: Spatial Table — Interactive Tangible (5 Jun) | Reel | Product Spotlight: Spatial Table — Interactive Tangible (5 Jun) | Post |  | Product Spotlight: Spatial Table — Interactive Tangible (5 Jun) | Abhirami | — | —
26 | Jun 8 | Mon | W8 | Phase 2: Product Push | Spatial Touch: interactive kiosks that convert visitors to leads (touch reel) | Spatial Touch: interactive kiosks that convert visitors to leads (touch reel) | Video | Spatial Touch: interactive kiosks that convert visitors to leads (touch reel) | Post | Spatial Touch: interactive kiosks that convert visitors to leads (touch reel) | Reel | Spatial Touch: interactive kiosks that convert visitors to leads (touch reel) | Video |  |  | Ankita | Sanath | Sooriya
27 | Jun 10 | Wed | W8 | Phase 2: Product Push | Spatial Touch: Kiosks That Let Buyers Explore (10 Jun) | Spatial Touch: Kiosks That Let Buyers Explore (10 Jun) | Post | Spatial Touch: Kiosks That Let Buyers Explore (10 Jun) | Post | Spatial Touch: Kiosks That Let Buyers Explore (10 Jun) | Reel | Spatial Touch: Kiosks That Let Buyers Explore (10 Jun) | Post | Spatial Touch: Kiosks That Let Buyers Explore (10 Jun) |  | Abhirami | — | —
28 | Jun 12 | Fri | W8 | Phase 2: Product Push | Product Spotlight: Spatial Touch — Interactive Kiosks (12 Jun) | Product Spotlight: Spatial Touch — Interactive Kiosks (12 Jun) | Post | Product Spotlight: Spatial Touch — Interactive Kiosks (12 Jun) | Post | Product Spotlight: Spatial Touch — Interactive Kiosks (12 Jun) | Reel | Product Spotlight: Spatial Touch — Interactive Kiosks (12 Jun) | Post |  | Product Spotlight: Spatial Touch — Interactive Kiosks (12 Jun) | Ankita | — | —
29 | Jun 15 | Mon | W9 | Phase 2: Product Push | Spatial Tour: VR station, one tablet controls multiple headsets (reel) | Spatial Tour: VR station, one tablet controls multiple headsets (reel) | Video | Spatial Tour: VR station, one tablet controls multiple headsets (reel) | Post | Spatial Tour: VR station, one tablet controls multiple headsets (reel) | Reel | Spatial Tour: VR station, one tablet controls multiple headsets (reel) | Video |  |  | Abhirami | Sanath | Sooriya
30 | Jun 17 | Wed | W9 | Phase 2: Product Push | Spatial Tour: Guided VR Walkthroughs (17 Jun) | Spatial Tour: Guided VR Walkthroughs (17 Jun) | Post | Spatial Tour: Guided VR Walkthroughs (17 Jun) | Post | Spatial Tour: Guided VR Walkthroughs (17 Jun) | Reel | Spatial Tour: Guided VR Walkthroughs (17 Jun) | Post | Spatial Tour: Guided VR Walkthroughs (17 Jun) |  | Ankita | — | —
31 | Jun 19 | Fri | W9 | Phase 2: Product Push | Product Spotlight: Spatial Tour — Guided VR (19 Jun) | Product Spotlight: Spatial Tour — Guided VR (19 Jun) | Post | Product Spotlight: Spatial Tour — Guided VR (19 Jun) | Post | Product Spotlight: Spatial Tour — Guided VR (19 Jun) | Reel | Product Spotlight: Spatial Tour — Guided VR (19 Jun) | Post |  | Product Spotlight: Spatial Tour — Guided VR (19 Jun) | Abhirami | — | —
32 | Jun 22 | Mon | W10 | Phase 2: Product Push | Spatial Holo — the Holobox, 3D hologram, no glasses (hologram video) | Spatial Holo — the Holobox, 3D hologram, no glasses (hologram video) | Video | Spatial Holo — the Holobox, 3D hologram, no glasses (hologram video) | Post | Spatial Holo — the Holobox, 3D hologram, no glasses (hologram video) | Reel | Spatial Holo — the Holobox, 3D hologram, no glasses (hologram video) | Video |  |  | Ankita | Sanath | Sooriya
33 | Jun 24 | Wed | W10 | Phase 2: Product Push | Spatial Holo: Holographic Scale Models (24 Jun) | Spatial Holo: Holographic Scale Models (24 Jun) | Post | Spatial Holo: Holographic Scale Models (24 Jun) | Post | Spatial Holo: Holographic Scale Models (24 Jun) | Reel | Spatial Holo: Holographic Scale Models (24 Jun) | Post | Spatial Holo: Holographic Scale Models (24 Jun) |  | Abhirami | — | —
34 | Jun 26 | Fri | W10 | Phase 2: Product Push | Product Spotlight: Spatial Holo — Holographic (26 Jun) | Product Spotlight: Spatial Holo — Holographic (26 Jun) | Post | Product Spotlight: Spatial Holo — Holographic (26 Jun) | Post | Product Spotlight: Spatial Holo — Holographic (26 Jun) | Reel | Product Spotlight: Spatial Holo — Holographic (26 Jun) | Post |  | Product Spotlight: Spatial Holo — Holographic (26 Jun) | Ankita | — | —
35 | Jun 29 | Mon | W11 | Phase 2: Product Push | Spatial Agent: AI avatar inside a Holobox, multilingual (AI demo video) | Spatial Agent: AI avatar inside a Holobox, multilingual (AI demo video) | Video | Spatial Agent: AI avatar inside a Holobox, multilingual (AI demo video) | Post | Spatial Agent: AI avatar inside a Holobox, multilingual (AI demo video) | Reel | Spatial Agent: AI avatar inside a Holobox, multilingual (AI demo video) | Video |  |  | Abhirami | Sanath | Sooriya
36 | Jun 30 | Tue | W11 | Phase 2: Product Push | Spatial Agent: 3 Ways AI Avatars Transform Real Estate Sales | 3 ways Spatial Agent transforms real estate — multilingual, always-on, inside a Holobox | Carousel | 3 ways AI avatars are changing how property gets sold. #SpatialAgent #PropTech | Post | [6 empty] | Ankita | — | —
37 | Jul 1 | Wed | W11 | Phase 2: Product Push | Spatial Agent Deep Dive — AI Concierge for Real Estate |  |  |  |  | Reel: Spatial Agent AI concierge — see it greet buyers in Arabic, Hindi & English | Reel | Spatial Agent: AI property concierge that speaks 40+ languages — watch the demo | Video | Spatial Agent: Your AI Property Concierge (1 Jul) |  | Ankita | Sanath | Sooriya, John
38 | Jul 2 | Thu | W11 | Phase 2: Product Push | Reality Capture: From Physical Space to Digital Twin in 48 Hours | Reality Capture: scan any building → digital twin in 48 hours. Here's how it works. | Carousel | Physical to digital in 48 hours. Reality Capture → Digital Twin pipeline. #PropTech | Post | [6 empty] | Ankita | — | —
39 | Jul 3 | Fri | W11 | Phase 2: Product Push | Product Spotlight: Spatial Agent + Reality Capture — Newsletter |  |  |  |  | Carousel: Reality Capture → Digital Twin workflow — before/after | Carousel | Reality Capture turns physical spaces into digital twins in 48 hours — see the process | Carousel |  | Product Spotlight: Spatial Agent + Reality Capture (3 Jul) | Abhirami | — | —
40 | Jul 6 | Mon | W12 | Phase 3: Deepening | Dubai Developer Case Study: Spatial Twin + Cave → 2.5x Off-Plan Conversion | Case Study: Dubai developer used Spatial Twin + Cave — off-plan conversion up 2.5x | Video | 2.5x off-plan conversion. One Dubai developer. Twin + Cave. Real numbers. #PROPVR | Post | [6 empty] | Ankita | Sanath | Sooriya, John
41 | Jul 7 | Tue | W12 | Phase 3: Deepening | Client Testimonial: How PROPVR Helped Sell 200 Units in 90 Days | Client testimonial: 'PROPVR helped us sell 200 units in 90 days' — watch the full story | Video | '200 units. 90 days. PROPVR made it happen.' — hear from our client. #RealEstate | Post | [6 empty] | Abhirami | Sanath | Sooriya, John
42 | Jul 8 | Wed | W12 | Phase 3: Deepening | Case Study Reel + Blog: Real Estate Results with Spatial OS |  |  |  |  | Reel: Dubai case study — 2.5x conversion with Spatial Twin + Cave | Reel | Case Study: How one developer doubled off-plan sales with immersive tech | Video | Real Estate Case Studies: How Developers Use Spatial OS (8 Jul) |  | Ankita | Sanath | Sooriya, John
43 | Jul 9 | Thu | W12 | Phase 3: Deepening | Founder's Note: The Customer Effect — Why We Build for Real Estate | Founder's Note: why every product we build starts with a real estate problem | Video | Every product we build starts with a real estate problem. Here's why. — Srinath, CEO #PROPVR | Post | [6 empty] | Ankita | Sanath | Sooriya, John
44 | Jul 10 | Fri | W12 | Phase 3: Deepening | Founder's Note IG/FB + Newsletter: Case Studies Edition |  |  |  |  | Reel: Founder's Note — 60s on why immersive tech matters for real estate | Reel | Founder's Note: the story behind PROPVR and why real estate needs spatial tech | Video |  | Real Estate Case Studies Edition (10 Jul) | Abhirami | — | —
45 | Jul 13 | Mon | W13 | Phase 3: Deepening | Industry Spotlight: Hospitality — How Hotels Use Spatial OS for Virtual Tours | How 5-star hotels use Spatial OS to let guests explore rooms before booking | Carousel | Hotels are letting guests walk through rooms in 3D before booking. Here's how. #Hospitality | Post | [6 empty] | Ankita | — | —
46 | Jul 14 | Tue | W13 | Phase 3: Deepening | Content Services Showcase: 3D Rendering + Animation + 360° + VR Movies + XR | Content Services: see what our studio delivers — 3D renders, animation, 360° tours, VR movies, XR | Video | Our content studio in one reel: 3D renders + animation + 360° + VR + XR. #ContentStudio | Post | [6 empty] | Abhirami | Sanath | Sooriya, John
47 | Jul 15 | Wed | W13 | Phase 3: Deepening | Hospitality + Content Services — IG/FB Repost + Blog |  |  |  |  | Carousel: How Spatial OS transforms hospitality — 5 use cases | Carousel | Content Services showreel: see what our Dubai studio creates for real estate brands | Video | Why 3D Visualization Works: The Psychology of Buying (15 Jul) |  | Ankita | — | —
48 | Jul 16 | Thu | W13 | Phase 3: Deepening | Industry Spotlight: Government & Smart Cities — Digital Twin Infrastructure | How governments use Digital Twins for smart city planning — from Dubai to Riyadh | Carousel | Smart cities need digital twins. Here's how govts in UAE and Saudi are building them. #SmartCities | Post | [6 empty] | Ankita | — | —
49 | Jul 17 | Fri | W13 | Phase 3: Deepening | Smart Cities IG/FB + Newsletter: 3D Visualization Deep Dive |  |  |  |  | Reel: Digital Twin of a smart city district — see the 3D model come alive | Reel | How digital twins are powering smart city planning in the Gulf — Spatial OS for government | Carousel |  | 3D Visualization Deep Dive (17 Jul) | Abhirami | Sanath | Sooriya, John
50 | Jul 20 | Mon | W14 | Phase 3: Deepening | Inside PROPVR's Experience Centre — Virtual Tour Part 1 | Welcome to the PROPVR Experience Centre — Part 1: Cave + Holo zones | Video | Step inside our Experience Centre. Cave. Holo. Twin. All in one space. #PROPVR #ExperienceCentre | Post | [6 empty] | Abhirami | Sanath | Sooriya, John
51 | Jul 21 | Tue | W14 | Phase 3: Deepening | ROI: 2.5x Conversion Lift + 40% Shorter Sales Cycle — The Numbers | ROI: 2.5x conversion lift, 40% shorter sales cycle — the numbers behind immersive tech | Carousel | 2.5x conversion. 40% shorter sales cycle. The ROI of immersive real estate tech. #PropTech | Post | [6 empty] | Ankita | — | —
52 | Jul 22 | Wed | W14 | Phase 3: Deepening | EC Tour + ROI — IG/FB Repost + Blog |  |  |  |  | Reel: Inside the PROPVR Experience Centre — 30s walkthrough | Reel | The ROI of immersive tech: real numbers from real clients — 2.5x conversion, 40% faster sales | Carousel | Inside a PROPVR Experience Centre: A Virtual Tour (22 Jul) |  | Ankita | Sanath | Sooriya, John
53 | Jul 23 | Thu | W14 | Phase 3: Deepening | Product Bundles: Starter / Pro / Enterprise — Which Stack Fits You? | 3 product bundles: Starter (Lite+Touch), Pro (Twin+Guide+Table), Enterprise (full ecosystem) | Carousel | Starter. Pro. Enterprise. 3 Spatial OS bundles — which one fits your sales gallery? #PROPVR | Post | [6 empty] | Ankita | — | —
54 | Jul 24 | Fri | W14 | Phase 3: Deepening | Product Bundles IG/FB + Newsletter: EC Tour + Bundles |  |  |  |  | Carousel: Which Spatial OS bundle is right for you? Starter vs Pro vs Enterprise | Carousel | Which Spatial OS bundle fits your business? Compare Starter, Pro, and Enterprise | Carousel |  | Experience Centre Virtual Tour + Product Bundles (24 Jul) | Abhirami | — | —

## Launch Campaign Month 1
🚀 LAUNCH CAMPAIGN — Daily LinkedIn (Apr 16 – May 19, 2026)
34 daily LinkedIn posts grouped into 12 themed blocks — 4 teaser days + 30-day reveal arc
Block | Dates | Days | Theme | What Gets Posted | Format | Video/Reel Assignee | Content/Copy Assignee
1 | Apr 16 – Apr 19 | 4 | Pre-Launch Teasers | 4-day countdown: "4 days → 3 days → 2 days → Tomorrow" | 2× Static + 2× Reel | Sooriya | Ankita
2 | Apr 20 – Apr 21 | 2 | Launch Reveal | Day 1: Spatial OS Ecosystem big reveal (hero video, pinned) Day 2: Ecosystem map — how all products connect | 1× Video + 1× Carousel | Sooriya | Ankita
3 | Apr 22 – Apr 26 | 5 | Spatial Products (5) | Spatial Lite → Spatial World → Spatial Twin ⭐ → Spatial Guide → Spatial Cities (Twin is flagship day — Whitepaper 1 drops) | Videos / Reels (all 5) | Sooriya | Ankita
4 | Apr 27 – Apr 30 | 4 | Experience Centre — Video Hardware (pt 1) | Spatial Holo 🌟 → Spatial Agent → Spatial Touch → Spatial Cave | Videos (all 4) | Sooriya | Ankita
5 | May 1 | 1 | Holiday — Labour Day 🎉 | International Labour Day post — cross-posted on LinkedIn + X + Instagram + Facebook | Static (4-channel post) | — | Ankita, Abirami
6 | May 2 – May 3 | 2 | Experience Centre — Video Hardware (pt 2) | Spatial Table → Spatial Tour | Videos (both) | Sooriya | Ankita
7 | May 4 – May 6 | 3 | Experience Centre — Static Hardware (images only) | Spatial Lens → Spatial Map → Spatial Drive (no video footage available — rely on product stills) | Carousels (all 3) | Sooriya | Ankita
8 | May 7 – May 8 | 2 | Solutions | Reality Capture (scan → twin workflow) → Digital Twins (Built + Unbuilt) (Whitepaper 2 drops: Giga Projects) | Carousels (both) | — | Ankita, Abirami
9 | May 9 | 1 | Content Services (clubbed) | One combined post covering 3D Render + Animation + 360° + VR Movies + XR — studio showreel | Mixed (Showreel or Carousel) | Sooriya | Ankita
10 | May 10 | 1 | Founder's Note | Personal to-camera video from founder — why we rebranded, vision for Spatial | Video (60–90s) | Sooriya | Ankita
11 | May 11 – May 17 | 7 | Industries (7) | Real Estate → Giga Projects → Hospitality → Govt & Smart Cities → Aviation → Maritime → Data Centres | Carousels (all 7) | — | Ankita, Abirami
12 | May 18 – May 19 | 2 | Culture + Recap | Day 33: Meet the team behind Spatial (work culture) Day 34: 30-Days-In recap — full ecosystem map with links | Mixed + Carousel | — | Ankita, Abirami
📄 SUPPORTING CONTENT ACROSS THE 34 DAYS
Asset | Count | Dates |  | Drops / Promo
Blog posts | 4 | Apr 22 · Apr 29 · May 6 · May 13 |  | Wed publish + Thu promo — Welcome · EC Pt 1 · EC Pt 2 · Industries
Newsletters | 4 | Apr 24 · May 1 · May 8 · May 15 |  | Fri send + Sat promo — Launch · EC · Solutions · Industries
Whitepaper drops | 2 | Apr 24 · May 8 |  | Gated downloads — Real Estate · Giga Projects
Cross-channel post | 1 | May 1 |  | LinkedIn + X + Insta + FB — Labour Day
🎬 FORMAT MIX ACROSS 34 POSTS
Format | Count | % Mix |  | Used For
Video / Reel | 17 | 50% | Products, EC video hardware, Founder, Launch hero
Carousel | 13 | 38% | EC static hardware, Solutions, Industries, Recap, Ecosystem map
Static | 3 | 9% | Teasers, Holiday post
Mixed | 1 | 3% | Content Services (studio showreel)

## Lead Gen Tracker
Week | Campaign | Asset / Offer | Primary Channel | Target Audience | Goal (Leads) | Leads Actual | Cost per Lead | Notes
W19 | Discovery Call Campaign | Free 30-min consultation | LinkedIn Ads + Email | RE developers UAE/Saudi/India | 50 |  |  | Launch week
W20 | EC Tour Push | Book a live EC tour | Instagram + LinkedIn + Retargeting | Warm leads | 40 |  |  | Urgency-driven
W21 | Live Webinar Registration | 45-min live showcase | LinkedIn + Email + Organic | B2B real estate leaders | 200 |  |  | Registrations → demo
W22 | Retargeting Success Stories | Client case studies + call | Retargeting | Website visitors, email openers | 60 |  |  | High-conviction
W23 | Partner Co-Marketing | Joint webinar or WP | LinkedIn + Partner channels | Partner audience + PROPVR | 80 |  |  | Leverage partner trust
W24 | End-of-Quarter Sales Push | Q3 pricing + priority deploy | All channels + ads | Existing pipeline + warm | 30 |  |  | Close before Sep 30
W25 | Q4 Early Access | Early access + beta pricing | LinkedIn + Email | Existing clients + top prospects | 50 |  |  | VIP positioning
W26 | Campaign Wrap + 2027 Teaser | Thank-you + 2027 signup | All channels | Full community | — |  |  | Q4/Q1 2027 pipeline

## KPI Tracker
Channel | KPI | Baseline | M1 | M2 | M3 | M4 | M5 | M6 | 6-Mo Target | 6-Mo Actual
LinkedIn | Followers
LinkedIn | Post Impressions
LinkedIn | Engagement Rate (%)
LinkedIn | Whitepaper Downloads
LinkedIn | Leads from LinkedIn
X | Followers
X | Impressions
X | Engagement Rate (%)
Instagram | Followers
Instagram | Reach
Instagram | Reel Views
Instagram | Saves
Facebook | Page Likes
Facebook | Post Reach
Facebook | Engagement Rate (%)
YouTube | Subscribers
YouTube | Watch Time (hrs)
YouTube | Views
Blog | Monthly Visitors
Blog | Avg Time on Page
Blog | Posts Published
Newsletter | Subscribers
Newsletter | Open Rate (%)
Newsletter | CTR (%)
Lead Gen | Discovery Calls Booked
Lead Gen | Demo Requests
Lead Gen | WP Downloads (total)
Lead Gen | Webinar Registrations
Lead Gen | Qualified Leads
Lead Gen | Closed Deals
Overall | Website Traffic
Overall | Traffic from Social
Overall | Cost per Lead

## Team Members
Name | Role | Responsibilities | Assigned Content Types | Reports To | Color Code
Sanath | Video Moodboard & Storyboard Lead | Creates moodboard/storyboard for all Video & Reel content Leads video creative direction Approves final video output | Video, Reel, Mixed (moodboard + storyboard) | — | #F59E0B (Amber)
Sooriya | Video & Reels Production | Video production and editing Reel creation for all platforms Works with Sanath on storyboard execution | Video, Reel, Mixed (production) | Sanath | #06D6A0 (Green)
Ankita | Content Lead — Video Captions + Shared Content | Content writing for Video reels (captions, copy, hooks) Share of Newsletter content Share of Blog post content Share of Carousel posts across all platforms | Video/Reel (content writing), Blog, Newsletter, Carousel, Static | — | #7C3AED (Purple)
Abirami | Content Creator — Shared Content | Share of Newsletter content Share of Blog post content Share of Carousel posts across all platforms | Blog, Newsletter, Carousel, Static | — | #3B82F6 (Blue)
John | Video Editor & Videographer (Dubai) | Video editing and post-production On-location videography in Dubai Product demo filming Client testimonial shoots | Video, Reel (editing + filming) | Sooriya / Sanath | #EF4444 (Red)
ASSIGNMENT RULES
Content Type | Assigned To | Reason
Video / Reel moodboard & storyboard | Sanath | Sanath leads creative direction for all video content
Video / Reel production | Sooriya (reports to Sanath) | Sooriya creates videos/reels under Sanath's direction
Video editing & filming | John (Dubai-based) | On-location filming + post-production editing
Video / Reel captions & copy | Ankita | Ankita writes all captions, hooks, and copy for videos
Blog posts | Ankita + Abirami (shared) | Both share long-form content writing
Newsletter editions | Ankita + Abirami (shared) | Both share newsletter copy and layout
Carousel posts | Ankita + Abirami (shared) | Both share carousel slide content
Static image posts | Ankita + Abirami (shared) | Both share static content and copy